## Launch Timeline
PRODUCT LAUNCH CHECKLIST & TIMELINE
Product/Feature: | [Product Name] | Launch Date: | [Date] | Owner: | [Name]
PRE-LAUNCH (T-30 to T-7 days)
Task | Description | Owner | Due Date | Status | Notes
Messaging & Positioning | Finalize core messaging, value props, and positioning statement | [Product Marketing] | [T-25] | Not Started
Target Personas | Confirm target buyer personas and use cases | [Product Marketing] | [T-25] | Not Started
Competitive Analysis | Review competitive landscape and differentiation | [Product Marketing] | [T-25] | Not Started
Blog Post Draft | Write launch announcement blog post | [Content Marketing] | [T-20] | Not Started
Email Campaigns | Design email sequences for customers and prospects | [Marketing] | [T-20] | Not Started
Sales Deck | Create sales enablement deck with talking points | [Product Marketing] | [T-18] | Not Started
Product Demo Video | Record demo video or walkthrough | [Product Marketing] | [T-18] | Not Started
Website Updates | Update product pages, features, and pricing | [Marketing] | [T-15] | Not Started
Sales Training | Schedule and prepare sales team training session | [Sales Enablement] | [T-15] | Not Started
Support Documentation | Create help docs, FAQs, and support materials | [Product/Support] | [T-12] | Not Started
Press Release | Draft press release (if applicable) | [PR/Marketing] | [T-10] | Not Started
Analyst Briefings | Schedule briefings with industry analysts | [Product Marketing] | [T-10] | Not Started
LAUNCH WEEK (T-7 to Launch Day)
Task | Description | Owner | Due Date | Status | Notes
Final Asset Review | Review all assets for accuracy and brand consistency | [Product Marketing] | [T-7] | Not Started
Sales Team Briefing | Conduct sales team training and Q&A session | [Sales Enablement] | [T-5] | Not Started
Customer Success Briefing | Train CS team on new features and common questions | [Customer Success] | [T-5] | Not Started
Support Team Briefing | Train support team on troubleshooting and FAQs | [Support] | [T-5] | Not Started
Blog Post Publish | Publish launch announcement blog post | [Content Marketing] | [T-3] | Not Started
Email Campaign Launch | Send launch announcement emails to segments | [Marketing] | [T-2] | Not Started
Social Media Posts | Schedule and publish social media announcements | [Marketing] | [T-1] | Not Started
Press Release Distribution | Distribute press release to media (if applicable) | [PR] | [Launch Day] | Not Started
Product Release | Enable feature/product for all customers | [Product/Engineering] | [Launch Day] | Not Started
Internal Announcement | Announce launch to internal team | [Product Marketing] | [Launch Day] | Not Started
POST-LAUNCH (Launch Day +1 to +30)
Task | Description | Owner | Due Date | Status | Notes
Monitor Metrics | Track adoption, engagement, and usage metrics | [Product Marketing] | [Ongoing] | Not Started
Collect Feedback | Gather feedback from early adopters and customers | [Product/CS] | [Ongoing] | Not Started
Sales Follow-up | Check in with sales team on deal conversations | [Sales Enablement] | [+3 days] | Not Started
Support Ticket Review | Review support tickets for common issues | [Support] | [+5 days] | Not Started
Case Study Outreach | Identify customers for case studies | [Customer Marketing] | [+7 days] | Not Started
Iterate Messaging | Refine messaging based on market feedback | [Product Marketing] | [+14 days] | Not Started
Launch Retrospective | Conduct post-launch retrospective meeting | [Product Marketing] | [+21 days] | Not Started
Quarterly Review | Review launch success metrics and learnings | [Product Marketing] | [+30 days] | Not Started

## RACI Matrix
RACI MATRIX - Cross-Functional Owners
R = Responsible | A = Accountable | C = Consulted | I = Informed
Task/Activity | Product Marketing | Product | Engineering | Sales | Marketing | Support/CS | PR | Notes
Messaging & Positioning | A | C |  | C | C |  |  | Product Marketing owns, others provide input
Blog Post | R | C |  |  | A |  | C | Marketing approves, Product Marketing writes
Sales Deck | A | C |  | C |  |  |  | Sales provides feedback
Product Demo Video | R | A | C | C |  |  |  | Product owns, Product Marketing creates
Website Updates | C | C |  |  | A |  |  | Marketing owns execution
Sales Training | A | C |  | C |  |  |  | Sales Enablement supports
Support Documentation | C | A | C |  |  | C |  | Product/Support own
Press Release | C | C |  |  | C |  | A | PR owns, others review
Analyst Briefings | A | C | [5 empty] | Product Marketing leads
Customer Communications | A |  |  |  | R | C |  | Marketing executes, Product Marketing approves
Metrics Tracking | A | C | C |  |  |  |  | Product Marketing owns analysis

## Asset Checklist
ASSET CHECKLIST
Asset | Owner | Due Date | Status | Published | Notes/Link
Blog Post - Launch Announcement | [Content Marketing] | [T-3] | Not Started
Blog Post - How It Works | [Content Marketing] | [T-7] | Not Started
Blog Post - Use Cases | [Content Marketing] | [T-10] | Not Started
Email - Customer Announcement | [Marketing] | [T-2] | Not Started
Email - Prospect Nurture | [Marketing] | [T-2] | Not Started
Sales Deck - Internal | [Product Marketing] | [T-18] | Not Started
Sales One-Pager | [Product Marketing] | [T-18] | Not Started
Product Demo Video | [Product Marketing] | [T-18] | Not Started
Website - Product Page | [Marketing] | [T-15] | Not Started
Website - Feature Page | [Marketing] | [T-15] | Not Started
Website - Pricing Page | [Marketing] | [T-15] | Not Started
Social Media - LinkedIn Post | [Marketing] | [T-1] | Not Started
Social Media - Twitter/X Post | [Marketing] | [T-1] | Not Started
Press Release | [PR] | [Launch Day] | Not Started
Support Documentation | [Product/Support] | [T-12] | Not Started
FAQ Document | [Product/Support] | [T-12] | Not Started
Release Notes | [Product] | [Launch Day] | Not Started
Analyst Briefing Deck | [Product Marketing] | [T-10] | Not Started

## Metrics Tracker
LAUNCH METRICS TRACKER
Metric | Baseline (Pre-Launch) | Week 1 | Week 2 | Week 4 | Notes
Product Adoption Rate |  |  |  |  | % of eligible customers using feature
Active Users |  |  |  |  | Number of users actively using feature
Feature Usage Frequency |  |  |  |  | Average uses per user per week
Blog Post Views |  |  |  |  | Total views on launch blog post
Email Open Rate |  |  |  |  | Open rate for launch announcement emails
Email Click Rate |  |  |  |  | Click rate for launch announcement emails
Sales Conversations |  |  |  |  | Number of deals mentioning new feature
Support Tickets |  |  |  |  | Support tickets related to new feature
Customer Feedback Score |  |  |  |  | NPS or satisfaction score for feature
Social Media Engagement |  |  |  |  | Likes, shares, comments on launch posts
Press Mentions |  |  |  |  | Number of press/analyst mentions
Website Traffic |  |  |  |  | Traffic to product/feature pages